## Product Backlog
Project Name | Orange HRM
Client | Astha Rokade
Created By | Astha Rokade
Creation Date | 2025-02-14
Approval Date | 2025-02-14
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
Build_bo1 | US_01 | Login Page | User Name,Text field ,Password text field and login button must be present Accepted UserName : Admin Accepted Password: admin123 | Fail | 1.User Name should enter valid username & Password. 2. Click on Login Button. 3. Home Page should be display
Build_bo2 | US_02 | Home Page | Home Page Element & Functionality Note. Home Page displays the expected elements and functionality. | Pass | 1. Home Page displays orange HRM logo. 2. Home Page displays clear and organized dashboard. 3.The user can click on metric to view more details. 4.The user can click on the link to navigate to another page.
Build_bo3 | US_03 | User Profile Page | User profile Page with Accurate information. | Pass | 1.The user profile page displays the users personal details. 2. The user profile page should allow to edit the personal details.
Build_bo4 | US_04 | Upgrade Page | Upgrade page title & available upgrade plans | Pass | 1.The Upgrade page displays the available upgrade option. 2.The Upgrade page displays Book a free demo box.
Build_bo5 | US_05 | Dashboard Page | Dashboard page Element & Functionality | Pass | 1.Dashboard Page should display the My action section. 2. User should able to click on all the elements under Quick Launch Section 3.The page should display the key performance indicators.
Build_bo6 | US_06 | Recruitment Functionality | Recruitement Page Elements & Functionality | Pass | 1.The page should Displays the Candidate information. 2.The page should Displays the Available Vacancies.
Build_bo7 | US_07 | Leave Mangement Functionality | Leave Page Elements & Functionality | Fail | 1. The all the elements on leave page should be clickable. 2.All the element on more option should be clickable and navigate to their page 3. User should be able to apply for a leave .
Build_bo8 | US_08 | Time Tracking Page | Time Tracking Elements & Functionality | Pass | 1.The timesheet pending action should be visible. 2.Attendance record should be clickable and visible.
Build_bo9 | US_09 | Buzz Page | Buzz page Elements & Functionality | Pass | 1. user should able to upload the post like photos ,videos. 2. All buttons in buzz page should be clickable.
Build_bo10 | US_10 | Logout Functionality | Validate logout Functionality | Pass | 1. User should able to click on the logout button and redirect to the main page
Build_bo11 | US_11 | Search Functionality | Validate the search Functionality | Pass | 1. User should able to search every element 2. User should able to click on the element
Epic-1

## Sprint Planning
Project Name | Orange HRM
Client | Excel R
Created By | Astha Rokade
Attendees | Astha Rokade
Creation Date | 2025-02-14
Epic | User Story ID | Feature/Title | User Story | Sprint | Status | Acceptance Creteria
Epic-1 | US_01 | Login Page | User Name,Text field ,Password text field and login button must be present Accepted UserName : Admin Accepted Password: admin123 | 1 | Fail | 1.User Name should enter valid username & Password. 2. Click on Login Button. 3. Home Page should be display
Epic-2 | US_02 | Home Page | Home Page Element & Functionality Note. Home Page displays the expected elements and functionality. | 2 | Pass | 1. Home Page displays orange HRM logo. 2. Home Page displays clear and organized dashboard. 3.The user can click on metric to view more details. 4.The user can click on the link to navigate to another page.
Epic-3 | US_03 | User Profile Page | User profile Page with Accurate information. | 3 | Pass | 1.The user profile page displays the users personal details. 2. The user profile page should allow to edit the personal details.
Epic-4 | US_04 | Upgrade Page | Upgrade page title & available upgrade plans | 4 | Pass | 1.The Upgrade page displays the available upgrade option. 2.The Upgrade page displays Book a free demo box.
Epic-5 | US_05 | Dashboard Page | Dashboard page Element & Functionality | 5 | Pass | 1.Dashboard Page should display the My action section. 2. User should able to click on all the elements under Quick Launch Section 3.The page should display the key performance indicators.
Epic-6 | US_06 | Recruitment Functionality | Recruitement Page Elements & Functionality | 6 | Pass | 1.The page should Displays the Candidate information. 2.The page should Displays the Available Vacancies.
Epic-7 | US_07 | Leave Mangement Functionality | Leave Page Elements & Functionality | 7 | Fail | 1. The all the elements on leave page should be clickable. 2.All the element on more option should be clickable and navigate to their page 3. User should be able to apply for a leave .
Epic-8 | US_08 | Time Tracking Page | Time Tracking Elements & Functionality | 8 | Pass | 1.The timesheet pending action should be visible. 2.Attendance record should be clickable and visible.
Epic-9 | US_09 | Buzz Page | Buzz page Elements & Functionality | 9 | Pass | 1. user should able to upload the post like photos ,videos. 2. All buttons in buzz page should be clickable.
Epic-10 | US_10 | Logout Functionality | Validate logout Functionality | 10 | Pass | 1. User should able to click on the logout button and redirect to the main page
Epic-11 | US_11 | Search Functionality | Validate the search Functionality | 11 | Pass | 1. User should able to search every element 2. User should able to click on the element

## Test scenarios
Project Name | Orange HRM
Module Name | OrangeHRM_Test_cases
Requirement Number | REQ001
Test case Type | Functionality , Usability , Integration Testings
Reference Doccument | NA
Pre-condition | Saucedemo URL should be accessible
Test Data | https://opensource-demo.orangehrmlive.com
Test Senario number | Description | Test Scenario Type | TE Name
User Story 1- Astha Rokade
TSH_01 | Validate Login Page Functionality | Functional Testing | Astha Rokade
User Story 1- Astha Rokade
TSH_02 | Validate Home Page Functionality | Functional Testing | Astha Rokade
User Story 1- Astha Rokade
TSH_03 | Validate User Profile Functionality | Functional Testing | Astha Rokade
User Story 1- Astha Rokade
TSH_04 | Validate the Upgrade Page Functionality | Functional Testing | Astha Rokade
User Story 1- Astha Rokade
TSH_05 | Validate Dashboard Page Functionality | Functional Testing | Astha Rokade
User Story 1- Astha Rokade
TSH_06 | Validate Requiremetn Page Functionality | Functional Testing | Astha Rokade
User Story 1- Astha Rokade
TSH_07 | Validate Leave Management Functionality | Functional Testing | Astha Rokade
User Story 1- Astha Rokade
TSH_08 | Validate Time Tracking Functionality | Functional Testing | Astha Rokade
User Story 1- Astha Rokade
TSH_09 | Validate Buzz Page Functionality | Functional Testing | Astha Rokade
User Story 1- Astha Rokade
TSH_10 | Validate the logout Functionality | Usability Testing | Astha Rokade
User Story 1- Astha Rokade
TSH_11 | Validate Search Functionality | Usability Testing | Astha Rokade
User Story 1- Astha Rokade

## Test cases
TE Name | Test case number | Test case name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | Priority | Tested By | Test Status | Test Creation Date | Test Execution Date | DEFECT NO
Astha Rokade | TC_01 | Verify the login functionality | Verify the behavior of the login functionality when a user enter valid login ID and validPassword then click on login button. | 1.Open the Orange HRM application 2.Enter Username & password with lower case. 3.Click on login button. | UserID : Admin Password:admin123 | User Should login to the Home Page | User logged in to the Home Page | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_02 | Verify the login functionality | Verify the behavior of the login functionality when a user enter only all Uppercase characters of loginID and valid password then click on login button. | 1.open the orange HRM application 2. Enter all uppercase characters of userID. 3.Enter valid password. 4.Click on login button. | UserID:ADMIN Password:admin123 | A pop up box of an error message should be visible. | A pop up box of an error message was not visible and user entered to home page. | High | Medium | Astha Rokade | Fail | 2025-02-14 | 2025-02-14 | TC_02_DT_001
Astha Rokade | TC_03 | Verify the login functionality | Verify the behavior of the login functionality when a user enter only all lowercase characters of loginID and valid password then click on login button. | 1.open the saucedemo application 2. Enter all lowercase characters of userID. 3.Enter valid password. 4.Click on login button. | UserID:admin Password:admin124 | A pop up box of an error message should be visible. | A pop up box of an error message was not visible and user entered to home page. | High | Medium | Astha Rokade | Fail | 2025-02-14 | 2025-02-14 | TC_03_DT_002
Astha Rokade | TC_04 | Verify Home Page Fucntionality | Verify the Home Functionality | 1.Login to Home Page |  | User Should be navigate to the Home Page | User Naviagated to the Home Page | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_05 | Verify Home Page Fucntionality | Verify the functionality of each and every element on the Home Page | 1.Click on the element of Home Page 2. check whterher user naviagate to new page |  | User should abe to click on the elements and navigate to new page | User was abe to click on the elements and navigate to new page | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_06 | Verify the user profile functionality | Verify the functionality of each and every element on the My info | 1.Click on the personal detail included in My info |  | User should be able to edit their personal detail | user was able to edit their personal detail | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_07 | Verify the user profile functionality | Verify the functionality of each and every element on the My info | 1.Click on the profile picture included in My info |  | User should able to Change their Profile Picture | User was able to change their profile picture | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_08 | Verify the user profile functionality | Verify the functionality of each and every element on the My info | 1.Enter alphabetical values in the zip code 2. Enter any letters in the state field. |  | User should get an error message "zip code accepets only numeric value" | user didn't get any error message | High | Medium | Astha Rokade | Fail | 2025-02-14 | 2025-02-14 | TC_08_DT_003
Astha Rokade | TC_09 | Verify the user profile functionality | Verify the functionality of each and every element on the My info | 1. Enter any numeric value in city or something else |  | User should get an error message"City field required a valid city name" | user didn't get any error message | High | Medium | Astha Rokade | Fail | 2025-02-14 | 2025-02-14 | TC_09_DT_004
Astha Rokade | TC_10 | Verify the user profile functionality | Verify the functionality of each and every element on the My info | 1.Click on the Qualification included in My info |  | User should be able to add and remove the qualification | user was able to add and remove the qualificartion | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_11 | Verify the Upgrade Page Functionality | Verify Upgrade to OrangeHRM Advanced! | 1.Click on the Book a free demo button |  | User should be able to click on the Booka a free demo button and fill their personal detail | user was able to click on the book a free demo button and filled their personal detail | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_12 | Verify the Upgrade Page Functionality | Verify Upgrade to OrangeHRM Advanced! | 1 . Enter the personal detail . |  | a pop up box of an error message should be visible while entering wrong email | a pop up box of an error message was visible while entering wrong email | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_13 | Verfiy the Dashboard page functionality | Verify the each and every web element on dashboard | 1. Click on element on Dashboard |  | User should be able to click on the elements in the dashboard and naviagate to that page | User was able to click on the elements in the dashboard and naviagate to that page | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_14 | Validate the Requirement Page Functionality | Verify the Requrement page Functionality | 1. Click on Candidate personal detail |  | User should be able to search the candidate by applying their detail | User was able to search the candidate by applying their detail | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_15 | Validate the Requirement Page Functionality | Verify the Requrement page Functionality | 1. Click on Candidate vacanices Button |  | User should able to add the vacancies | User was able to add the vacancies | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_16 | Validate the Requirement Page Functionality | Verify the Requrement page Functionality | 1. Click on Candidate personal detail |  | User should be able to search the new vacancies which was added reccently | User was not able to search the vacancies which were added recently | High | Medium | Astha Rokade | Fail | 2025-02-14 | 2025-02-14 | TC_16_DT_005
Astha Rokade | TC_17 | Validate the leave management functionality | Verify the Leave Management Functionality | 1.Click on all the tabs under leave Management 2.Check every tab working properly |  | User should be able to click on all the web elements under leave tab and navigate accordingly. | User was able to click on all the web elements under leave tab and navigate accordingly. | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_18 | Validate the Time Tracking Functionality | Verify the Time Tracking Functionality | 1.Click on Time tab 2. Check each and every web element under time functionality. |  | User should be able to create the new timesheet and edit the timesheet . | User was able to create new timesheet & edit the timesheet | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_19 | Validate the Buzz page functionality | Verify the Buzz Page Functionality | 1.Click on share image or share photos /post |  | User should able to share post with photos in png,jpg format | user was able to share post with photos in png,jpg format | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_20 | Validate the Buzz page functionality | Verify the Buzz Page Functionality | 1.Click on share video . |  | User should able to share url of video with caption | User was able to share url of video with caption | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_21 | Validate the Buzz page functionality | Verify the Buzz Page Functionality | 1.Click on share post |  | User should able to share the post | User was not able to share the post | High | Medium | Astha Rokade | Fail | 2025-02-14 | 2025-02-14 | TC_14_DT_006
Astha Rokade | TC_22 | Validate the logout functionality | Verify log out functionality | 1.Click on logout option |  | User should be able to logout the page and navigate to the login page | User was able to logout the page and navigate to the login page | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14
Astha Rokade | TC_23 | Validate the search functionality | Verify the search functionality | 1. Click on search tab 2. search different option given in menu |  | User should able to search the item or options | User was able to search the item or options | Medium | High | Astha Rokade | pass | 2025-02-14 | 2025-02-14

## Defects
TE Name | Defect number | Project Name | Module Name | Requirement Number | Test Case ID | Summary | Description | Issues | Severity | Priority | Assign to | Screen Shots
Astha Rokade | TC_02_DT_001 | Orange HRM | Login Functionality | REQ001 | TC_02 | A pop up box of an error message should be visible after entering incorrect login id. | Verify the behavior of the login functionality when a user enter only Uppercase characters of loginID and valid password then click on login button. | The user was able to login with incorrect LoginID | High | Medium | Astha Rokade
Astha Rokade | TC_03_DT_002 | Orange HRM | Login Functionality | REQ002 | TC_03 | A pop up box of an error message should be visible after entering incorrect login id. | Verify the behavior of the login functionality when a user enter only lowercase characters of loginID and valid password then click on login button. | The user was able to login with incorrect LoginID | High | Medium | Astha Rokade
Astha Rokade | TC_08_DT_003 | Orange HRM | My Info Functionality | REQ003 | TC_08 | User should get an error message "zip code accepets only numeric value" | Verify the functionality of each and every element on the My info | user didn't get any error message | High | Medium | Astha Rokade
Astha Rokade | TC_08_DT_004 | Orange HRM | My Info Functionality | REQ004 | TC_09 | User should get an error message"City field required a valid city name" | Verify the functionality of each and every element on the My info | user didn't get any error message | High | Medium | Astha Rokade
Astha Rokade | TC_16_DT_005 | Orange HRM | My Info Functionality | REQ005 | TC_16 | User should be able to search the new vacancies which was added reccently | Verify the Requrement page Functionality. Click on Candidate personal detail | User was not able to search the vacancies which were added recently | High | Medium | Astha Rokade

## Defect_Snapshots
Defect ID | Test Case ID | Failed Screenshots
TC_02_DT_001 | TC_02
TC_03_DT_002 | TC_03
TC_08_DT_003 | TC_08
TC_08_DT_004 | TC_09
TC_16_DT_005 | TC_16

## Test excution details
Test Case ID | Test Case Name | Screenshots | TestCase Execution Date | TestCase Execution Start Time | TestCase Execution END Time
TC_02 | Verify the login functionality |  | 2025-02-14 | 11:00 | 11:03
TC_03 | Verify the login functionality |  | 2025-02-14 | 11:05 | 11:10
TC_08 | Verify the user profile functionality |  | 2025-02-14 | 12:00PM | 12:10
TC_09 | Verify the user profile functionality |  | 2025-02-14 | 12:20 | 12:35
TC_16 | Validate the Requirement Page Functionality |  | 2025-02-14 | 12:39 | 12:50
TC_62

## Story_Point_Effort_and_Reason
User Story1-Astha Rokade
Project Name :- | Orange HRM
Story Point :- | 2
Reason for story point :- | User is able to click on login button and to see home page
Efforts(in hours) :- | 5
Reason for Efforts :- | Test cases Preparation:3 Test case excecution:1 Raising Bugs:5

## Test report
SNO | TE NAME | TOTAL TEST CASE | PASS | FAIL | BLOCKERS | NOT EXECUTED | PASS RATIO (%) formula use : D2/C2*100 | TEST IN PROGRESS | DEV IN PROGRESS | DONE | TOTAL DEFECT
1 | Astha Rokade | 23 | 18 | 5 | 0 | 0 | 78.26 | 0 | 0 | 23 | 5
TOTAL |  | 23 | 18 | 5 | 0 | 0 | 78.26 | 0 | 0 | 23 | 5